## BernCo-ABQ
BERNCO/CABQ Opioid Settlement Fund Workplan
Vital Strategies Recommendation 15: Leveraging the Sobering Center | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Support crisis stabilization centers that serve as alternative to emergency department by integration into medical sobering services, medication-assisted treatment (MAT), 24-hour first responder dropoff, medical respite, peer support services, and wrap around services. | CABQ | Bernco, Non-profit providers, peer support workers, partner agencies | 0-6 Months | December 2024 | 2111250
Vital Strategies Recommendation 19: Naloxone Access Expansion | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Expand Street Medicine Program from 1 Team to 4 Over 3 years | BernCo | UNMH | Year 1, 2, & 3 |  | 1855130
2. Expand Naloxone Vending Machines From 2 to 50 (16 per year over 3 Years) | BernCo | DBH | Years 1, 2, 3 |  | 1980000
3. Equipping all responder vehicles and maintain backstock for ACS, AFR, APD | CABQ |  | 0-6 Months | January 2025 | 400000
4. Installation of 25 vending machines at strategic locations that provide social services | CABQ | State of NM Dept. of Health, Non-profit providers, partner agencies | 0-6 Months | March 2025 | 990000
Vital Strategies Recommendation 13: Expand Mobile Crisis Response Services | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Implement one Mobile Response and Stabilization Service (MRSS) | BernCo | All Faiths | Year 1 |  | 670000
2. Expand to a Total of 4.3 MRSS Teams for 24/7/365 Coverage | BernCo | UNMH/All Faiths | Year 2 and 3 |  | 2190470
Vital Strategies Recommendation 23: Community-Based Treatment Access & Quality | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Community-Oriented Recovery (COR) Program | CABQ | State of NM Healthcare Authority, Providers, BernCo | 0-24 Months | July 2025 | 760000
2. Expand Albuquerque Fire & Rescue Personnel for Medication for Opioid Use Disorder (MOUD) | CABQ | BernCo FR, Abq Ambulance Services | 0-24 Months | December 2024 | 2028959
3. ECHO Care Coordination Project | BernCo | DBH/ECHO | Year 1 |  | 250000
4. Service Provider Care Coordination Capacity & Infrastrucure Project | BernCo | DBH | Years 1, 2, & 3 |  | TBD
6. Transportation Initiative | BernCo | TBD | TBD | TBD | TBD
Vital Strategies Recommendation 25: Recovery Housing | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Build and Operate a 2nd Tiny Home Villiage | BernCo | DBH | Year 2 |  | 5000000
| BernCo | DBH | Year 3 |  | 1500000
2. Eviction Prevention, Intervention, & Recovery Program (Proj. Mgr. Year 1) | BernCo | DBH & DCS | Years 1, 2, & 3 |  | 3725000
3. Expand recovery housing options for IOPs and provide housing for people w/ OUD and any co-occurring SUD & mental health conditions | CABQ | Non-profit providers, peer support workers, partner agencies | 0-24 Months |  | 8197337.45
Vital Strategies Recommendation 27: Peer Support Expansion | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. BernCo Peer Empowerment Center | BernCo | DBH | Years 1, 2, & 3 |  | 1500000
2. Expand peer support programs through HHH & ACS for persons w/ OUD and any co-occurring SUD & mental health conditions | CABQ |  | 0-24 Months | January 2025 | 3700000
Vital Strategies Recommendation 16: Comprehensive Education | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Keep NM Alive | BernCo | DGS/DBH | Years 1, 2,& 3 |  | 1335000
2. Implement and Sustain Elementary Level EBP | BernCo | APS | Years 1, 2, & 3 |  | TBD
3. Implement Olweus Bulling Prevention Program; 1 MS & 1 HS | BernCo | APS | Year 3 |  | 17000
4. Using the Restorative Justice Program and other city programming, train APS personnel on trauma-informed approaches to youth subtance use | CABQ | APS | 0-24 Months | July 2025 | 300000
5. Integrate prevention curricula at community centers & enhance programming for families | CABQ | Non-profits | 0-24 Months | July 2025 | 175000
Vital Strategies Recommendation 17: Connecting Disconnected Youth | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Expand School-Based Violence Intervention Program to include substance use treatement and additional schools served. | CABQ | APS | 0-24 Months | July 2025 | 1300000
2. Partner w/ communinty organizations to offer mentorship, re-engagement, and job training to youtg disconnected from education and work | CABQ | APS, CYFD | 0-24 Months | July 2025 | 762500
*BernCo Projects that also meet Recommendation 17
|  |  |  | Total BernCo | 20022600
|  |  |  | Total CABQ | 20725046.45

## BernCo
BERNCO Opioid Settlement Fund Workplan
Vital Strategies Recommendation 15: Leveraging the Sobering Center | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
Vital Strategies Recommendation 19: Naloxone Access Expansion | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Expand Street Medicine Program from 1 Team to 4 Over 3 years | BernCo | UNMH | Year 1, 2, & 3 |  | 1855130
2. Expand Naloxone Vending Machines From 2 to 50 (16 per year over 3 Years) | BernCo | DBH | Years 1, 2, 3 |  | 1980000
Vital Strategies Recommendation 13: Expand Mobile Crisis Response Services | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Implement one Mobile Response and Stabilization Service (MRSS) | BernCo | All Faiths | Year 1 |  | 670000
2. Expand to a Total of 4.3 MRSS Teams for 24/7/365 Coverage | BernCo | UNMH/All Faiths | Year 2 and 3 |  | 2190470
Vital Strategies Recommendation 23: Community-Based Treatment Access & Quality | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
3. ECHO Care Coordination Project | BernCo | DBH/ECHO | Year 1 |  | 250000
4. Service Provider Care Coordination Capacity & Infrastrucure Project | BernCo | DBH | Years 1, 2, & 3 |  | TBD
6. Transportation Initiative | BernCo | TBD | TBD | TBD | TBD
Vital Strategies Recommendation 25: Recovery Housing | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Build and Operate a 2nd Tiny Home Villiage | BernCo | DBH | Year 2 |  | 5000000
| BernCo | DBH | Year 3 |  | 1500000
2. Eviction Prevention, Intervention, & Recovery Program (Proj. Mgr. Year 1) | BernCo | DBH & DCS | Years 1, 2, & 3 |  | 150000
Vital Strategies Recommendation 27: Peer Support Expansion | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. BernCo Peer Empowerment Center | BernCo | DBH | Years 1, 2, & 3 |  | 1500000
Vital Strategies Recommendation 16: Comprehensive Education | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Keep NM Alive | BernCo | DGS/DBH | Years 1, 2,& 3 |  | 1335000
2. Implement and Sustain Elementary Level EBP | BernCo | APS | Years 1, 2, & 3 |  | TBD
3. Implement Olweus Bulling Prevention Program; 1 MS & 1 HS | BernCo | APS | Year 3 |  | 17000
Vital Strategies Recommendation 17: Connecting Disconnected Youth | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
*BernCo Projects that also meet Recommendation 17
|  |  |  | Total BernCo | 16447600

## ABQ
CABQ Opioid Settlement Fund Workplan
Vital Strategies Recommendation 15: Leveraging the Sobering Center | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Support crisis stabilization centers that serve as alternative to emergency department by integration into medical sobering services, medication-assisted treatment (MAT), 24-hour first responder dropoff, medical respite, peer support services, and wrap around services. | CABQ | Bernco, Non-profit providers, peer support workers, partner agencies | 0-6 Months | December 2024 | 2111250
Vital Strategies Recommendation 19: Naloxone Access Expansion | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
3. Equipping all responder vehicles and maintain backstock for ACS, AFR, APD | CABQ |  | 0-6 Months | January 2025 | 400000
4. Installation of 25 vending machines at strategic locations that provide social services | CABQ | State of NM Dept. of Health, Non-profit providers, partner agencies | 0-6 Months | March 2025 | 990000
Vital Strategies Recommendation 13: Expand Mobile Crisis Response Services | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
Vital Strategies Recommendation 23: Community-Based Treatment Access & Quality | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Community-Oriented Recovery (COR) Program | CABQ | State of NM Healthcare Authority, Providers, BernCo | 0-24 Months | July 2025 | 760000
2. Expand Albuquerque Fire & Rescue Personnel for Medication for Opioid Use Disorder (MOUD) | CABQ | BernCo FR, Abq Ambulance Services | 0-24 Months | December 2024 | 2028959
Vital Strategies Recommendation 25: Recovery Housing | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
3. Expand recovery housing options for IOPs and provide housing for people w/ OUD and any co-occurring SUD & mental health conditions | CABQ | Non-profit providers, peer support workers, partner agencies | 0-24 Months |  | 8197337.45
Vital Strategies Recommendation 27: Peer Support Expansion | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
2. Expand peer support programs through HHH & ACS for persons w/ OUD and any co-occurring SUD & mental health conditions | CABQ |  | 0-24 Months | January 2025 | 3700000
Vital Strategies Recommendation 16: Comprehensive Education | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
4. Using the Restorative Justice Program and other city programming, train APS personnel on trauma-informed approaches to youth subtance use | CABQ | APS | 0-24 Months | July 2025 | 300000
5. Integrate prevention curricula at community centers & enhance programming for families | CABQ | Non-profits | 0-24 Months | July 2025 | 175000
Vital Strategies Recommendation 17: Connecting Disconnected Youth | Responsible Party | Collaborators | Implementation Timeline | Projected Start Date | Projected Cost
1. Expand School-Based Violence Intervention Program to include substance use treatement and additional schools served. | CABQ | APS | 0-24 Months | July 2025 | 1300000
2. Partner w/ communinty organizations to offer mentorship, re-engagement, and job training to youtg disconnected from education and work | CABQ | APS, CYFD | 0-24 Months | July 2025 | 762500
*BernCo Projects that also meet Recommendation 17
|  |  |  | Total CABQ | 20725046.45

## Allocation
Bernco/CABQ Combined |  |  | Bernco/CABQ Individual
Crisis Response | 4971720 | 12.2% | Crisis Response ABQ | 2111250 | 10.19%
Prevention | 3889500 | 9.545% | Crisis Response BernCo | 2860470 | 14.29%
Harm Reduction | 5225130 | 12.82% | Prevention ABQ | 2537500 | 12.24%
Treatment | 3038959 | 7.458% | Prevention BernCo | 1352000 | 6.752%
Recovery | 18422337.45 | 45.21% | Harm Reduction ABQ | 1390000 | 6.707%
Peer Support | 5200000 | 12.76% | Harm Reduction BernCo | 3835130 | 19.15%
|  |  | Treatment ABQ | 2788959 | 13.46%
Total | 40747646.45 |  | Treatment BernCo | 250000 | 1.249%
|  |  | Recovery ABQ | 8197337.45 | 39.55%
|  |  | Recovery BernCo | 10225000 | 51.07%
|  |  | Peer Support ABQ | 3700000 | 17.85%
|  |  | Peer Support BernCo | 1500000 | 7.492%
|  |  | Total | 40747646.45